## Climate Action Plan Old (hidden)
Ref | Category | Action | Job Title | Carbon reduction impact | Status | Comments
1 | Funding | Obtain approval from SLT & CC Member Sub-Group for £150,000 spend on climate change mitigation & adaptation actions for financial years 2020/21, 2021/22 & 2022/23 | Service Manager (b/repairs & C/change) | High | Complete
2 | Funding | Determine budget for climate action annually and obtain approval from SLT | Service Manager (b/repairs & C/change) | High | Ongoing
3 | Funding | Publish a quarterly summary on 'One Welwyn Hatfield' website on achieved climate change action. | Communications and Marketing Manager | Low | Ongoing | Ongoing target
4 | Funding | Carry out a financial mapping exercise to identify opportunities to raise additional funds for decarbonisation projects e.g. what grants or loans are available? | Climate Change Officer | Low | In progress
5 | Funding | Identify and engage with community groups and other stakeholders who may be able to access funding for decarbonisation projects that is unavailable to local authorities | Climate Change Officer | Low | In progress
6 | Funding | Promote Sustainable Warmth grant scheme to residents on an income below £30,000 and in an EPC rated property E - G to encourage works in 50 homes within the borough | Service Manager (b/repairs & C/change) | High | Ongoing
7 | Governance | Develop a Procurement Strategy that ensures that social, economic, environmental and climate change issues are considered in all procurements | Procurement Manager | Medium | Complete
8 | Governance | Develop Local Plan and Local Transport Plan policies that facilitate a significant uptake in cyclying by improving safety, travel routes and storage facilities. | Senior Projects Officer (Planning) | High | Complete
9 | Governance | Include sustainability and carbon reduction requirements as part of the assessment criteria for all procurements | Procurement Manager | Medium | Ongoing
10 | Governance | Develop an Extreme Weather Plan for both hot and cold weather scenarios | Service Director (Residents & Neighbourhoods) | Low | Complete
11 | Governance | Ensure that all committee reports include section on climate change implications | Governance Services Manager | Medium | Complete
12 | Governance | Provide carbon literacy training for all councillors | Economic Development Officer | Low | Complete
13 | Governance | Organise voluntary carbon literacy training for local authority officers as a trial | Economic Development Officer | Low | Complete
14 | Governance | Roll out carbon literacy training to all local authority staff and Members | Economic Development Officer | Medium | Complete
15 | Governance | Identify joint work programmes with the other district councils in Hertfordshire, Herts County Council and Herts LEP via involvement in the Herts Climate Change and Sustainability Partnership | Service Manager (b/repairs & C/change) | High | Ongoing
16 | Governance | Webcast all committee meetings | Service Manager (b/repairs & C/change) | Low | Ongoing
17 | Governance | Calculate the council's own carbon emissions (Scopes 1, 2, and 3) at least annually to check if emissions are being reduced | Service Manager (b/repairs & C/change) | Low | Ongoing
18 | Engagement | Carry out 6 workshops with local businesses, community groups and landlords on how to effectively support decarbonisation. | Economic Development Officer | Medium | Complete
19 | Planning | Develop local plan policies that support sustainable design and construction principles | Assistant Director (Planning) | Medium | Complete
20 | Engagement | Enagage with local residents & workers to gather their opinions and ideas on air pollution, green jobs, food security and fuel poverty. | Env Health Technical Officer | Low | In progress
21 | Engagement | Develop a clear communications strategy that includes social media engagement, case study examples, leaflets and posters highlighting the work the council is doing, why it matters and how residents can contrbute. | Corporate Strategy & Engagement Manager | Low | In progress | In development - to be approved May/June
22 | Engagement | Add a 'latest news' feature to the climate change section of the website. | Corporate Strategy & Engagement Manager | Low | Complete | Progress made' sections on ONE website
23 | Engagement | Review 'nudge' behaviour theory and use it to identify opportunities to facilitate behaviour change such as publicising walk/cycle to school days. | Climate Change Officer | Low | In progress | Work with Comms and Engagement
24 | Procurement | Purchase only 100% recycled paper for use in WHBC printers | Corporate Support | Low | Complete
25 | WHBC emissions | Implement agile working arrangements for most WHBC staff | Executive Director (Finance & Transformation) | Medium | Complete
26 | WHBC emissions | Ensure that New Hatfield Commons multi-storey car park includes low energy features and 8 electric vehicle charge points | Parking and Playground Services Manager | High | Complete
27 | WHBC emissions | Bid into Public Sector Decarbonisation Scheme to replace gas boilers with air/water source heat pumps and install solar panels at Campus East, Campus West and Hatfield Swim Centre to reduce the carbon footprint. | Service Manager (b/repairs & C/change) | High | Complete
28 | Planning | Develop local plan policies that support the achievement of BREEAM Excellent standard for new non-residential buildings | Assistant Director (Planning) | Medium | Complete
29 | Planning | Carry out a sustainability appraisal and habitats assessment of the submitted local plan. | Assistant Director (Planning) | Medium | Complete
30 | Planning | Carry out a viability assessment of the policies in in the local plan to ensure that they are not prohibitively expensive for developers | Assistant Director (Planning) | Low | Complete
31 | Planning | Ensure that all future planning applications are scrutinised and encouraged to go beyond minimium standards to improve their long term sustainability, reduce embodied and operational carbon footprint and increase resilience to the impacts of climate change. | Assistant Director (Planning) | High | Ongoing | This takes place on an application by application basis, and subject to appropriate policy requirements. Hertfordshire Growth Board is producing a Developer Charter which, and seeking developers to support this. This would commit developers to delivering above Building Control stadards in these areas.
32 | Biodiversity | Develop local plan policies that: protect the countryside, open spaces, parks and green spaces; enhances the borough's critical environmental assets; creates and enhances green infrastructure links across the borough; protects and enhances ecological networks and biodiversity assets. | Assistant Director (Planning) | High | Complete
33 | Biodiversity | Purchase ecological advice from Herts CC to inform Local Plan policies and planning decisions | Assistant Director (Planning) | Medium | Ongoing | This continues for applications which meet relevant criteria.
34 | Biodiversity | Maintain up-to-date Tree Strategy to guide management of woodlands and street trees | Landscape and Ecology Manager | Medium | Ongoing | Targeting June Cabinet
35 | Biodiversity | Ensure that tree Officers attend Herts Tree Health Network to learn, monitor, report and take action on pests and diseases related to tree health | Landscape and Ecology Manager | Low | Ongoing
36 | Biodiversity | Plant and maintain flowers in key town centre locations | Environment Services Manager | Low | Ongoing
37 | Biodiversity | Plant and maintain wildflower meadows along key roads | Environment Services Manager | Low | Ongoing
38 | Biodiversity | Manage and let WHBC stock of allotment plots | Landscape and Ecology Manager | Low | Ongoing
39 | Biodiversity | Contribute to HCCSP biodiversity baseline study | Assistant Director (Planning) | Low | Ongoing | Ongoing
40 | Biodiversity | Contribute to preparation of Herts Green Infrastructure Strategy | Assistant Director (Planning) | High | Ongoing | Ongoing
41 | Transport | Continue to work with Herts County Council to implement policies in Local Transport Plan and other transport plans | Assistant Director (Planning) | Medium | Complete
42 | Transport | Ensure Local Plan policies include provision for pedestrians, cyclists, public transport and electric vehicles | Assistant Director (Planning) | Medium | Complete
43 | Transport | Develop a Green Travel Plan for council buildings and update it at least annually | Assistant Director (Planning) | Low | Complete
44 | Transport | Support the A414 Group to investige the merits of mass rapid transit options | Assistant Director (Planning) | Medium | Complete
45 | Transport | Support the Intalink Partnership to encourage greater bus patronage | Assistant Director (Planning) | Medium | Complete
46 | Transport | Apply for Government funding for new electric vehicle charge points in council-owned car parks as and when funding is available | Parking and Playground Services Manager | Medium | Complete
47 | Transport | Support the Living Lab project to trial electric and driverless vehicles in Hatfield business park | Assistant Director (Planning) | Low | Complete
48 | Transport | Review car parking charges as part of budget setting process with a view to generating a budget to invest in new green transport options. | Parking and Playground Services Manager | Low | Complete
49 | Transport | Work with Herts County Council to prepare Walking and Cycling Improvement Plan for Welwyn Garden City and Hatfield | Senior Projects Officer (Planning) | Medium | In progress
50 | Transport | Approve and publish Local Plan and Local Transport Plan policies that facilitate a significant uptake in cyclying by improving safety, travel routes and storage facilities. | Senior Projects Officer (Planning) | Medium | In progress
51 | Council Housing | Make it council policy to take a 'fabric first' approach to council house retrofit | Service Manager (Investment P/Delivery) | High | Complete
52 | Council Housing | Bid to Government's Green Homes Grant to improve EPC rating of 32 council houses | Housing | Medium | Complete
53 | Council Housing | Commission a study to investigate the magnitude of carbon emissions from council housing stock | Service Manager (b/repairs & C/change) | High | In progress | This will be completed following the completion of the 1 year stock condition surveys and EPCs by 31/03/24. The EPC surveys will assist in calculating the baseline figure
54 | Water | Ensure that Local Plan policies state that new homes must achieve water consumption of 110 litres per person per day | Assistant Director (Planning) | Low | Complete
55 | Water | Ensure that Local Plan policies state that development should consider flood risk and surface water management | Assistant Director (Planning) | Low | Complete
56 | Waste | Ensure that guidance on household waste collections is available and clearly signposted on WHBC website | Environment Services Manager | Medium | Complete
57 | Water | Complete actions in HCCSP Water Action Plan | Assistant Director (Planning) | Low | Complete | This Action Plan is now adopted
58 | Waste | Install recycling bins throughout council offices | Senior Building Surveyor | Low | Complete
59 | Waste | Phase out the use of disposable cups in council facilities | Senior Building Surveyor | Low | Complete
60 | Waste | Ensure that councillors use tablets and officers use laptops for all council meetings rather than printed papers | Governance Services Manager | Low | Complete
61 | Waste | Ensure that council target to recycle 50% of household waste is being met | Environment Services Manager | Medium | Ongoing
62 | Waste | Support Herts Waste Partnership Waste Aware Group by promoting its campaigns | Environment Services Manager | Low | Ongoing
63 | Waste | Attend 6 events per year at schools and other educational providers to promote WHBC waste initiatives | Environment Services Manager | Medium | Ongoing
64 | Waste | Consider the merits of raising the 50% recycling target to 55% to match the national target fo 2025. | Environment Services Manager | Low | Ongoing
65 | Pollution | Develop Local Plan policies that prevent development from having unacceptable impacts on the environment and human health | Service Manager (b/repairs & C/change) | Medium | Complete
66 | Engagement | Communicate WHBC's climate change actions by publishing at least 2 social media posts per month | Corporate Strategy & Engagement Manager | Low | Ongoing | Ongoing target
67 | Engagement | Add links to carbon footprint calculators that residents can use to calculate their own emissions to council website | Corporate Strategy & Engagement Manager | Low | Complete
68 | Engagement | Promote public transport, walking and cycling as alternative to driving by through public enagament and internally | Corporate Strategy & Engagement Manager | Medium | Ongoing | Internally via Winnie and TeamTalk; externally via ONE website and social media - to be incorporated into #20 and #69
69 | Engagement | Develop a comprehensive communication and engagement plan for residents and businesses to explain impacts of climate change, provide information on the actions the council is taking, and to influence behaviours on a variety of aspects which will lead to positive impacts on climate change. | Corporate Strategy & Engagement Manager | Medium | In progress | As above (merge this target with #20?)
70 | WHBC Emissions | Examine data from North and East Herts District Councils' consultation with residents on residual waste collection and use it to inform WHBC's decision on moving to less frequent collections at the end of the current waste contract (links to Action 130). | Environment Services Manager | Low | In progress
71 | Council Housing | Ludwick Way & Commons - 10 family homes , air source heat pumps, solar panels , water saving systems e.g toilet cistern , fabric first approach , EV charging points | Housing & Development Strategy Services Manager | Medium | In progress
72 | Council Housing | Howlands House and Burfield Close temporary accomdation schemes , 116 homes , which will include , air source heat pumps , solar panels, water saving devices , fabric first approach , mechanical ventilaition and heat recovery , EV car sharing points | Housing & Development Strategy Services Manager | Medium | In progress
73 | Council Housing | Review of all financial appraisals for the inclusion of green technologies in all new builds | Housing & Development Strategy Services Manager | Medium | In progress
74 | Council Housing | Include Climate Change agenda in the affordable homes design brief and set out design standards including Future Homes Standard and incorporating uplift in Building Regulations | Housing & Development Strategy Services Manager | Medium | In progress
75 | WHBC Emissions | Investigate the most suitable carbon removal offsetting options | Service Manager (b/repairs & C/change) | Low | Ongoing
76 | Council Housing | Develop a progamme of retrofit assessments across housing stock which will help identify decarbonisation and energy efficency measures required on our lowest performing homes. Following assessments we will add the actions to the action plan | Service Manager (Investment P/Delivery) | High | In progress | This will be completed following the completion of the 1 year stock condition surveys and EPCs by 31/03/24.
77 | Biodiversity | Plant 300 street trees (of appropriate species and in appropriate locations) per year until WHBC | Landscape and Ecology Manager | Medium | Complete | 316 trees planted
78 | Biodiversity | Identify council owned land for enhanced tree planting | Estates | High | Complete
79 | Water | Implement actions to reduce water consumption in council buildings based on the outcome of the investigation | Senior Building Surveyor | Low | Ongoing
80 | WHBC Emissions | Implement the energy efficiency measures identified by the investment grade energy audits of council owned buildings | Service Manager (b/repairs & C/change) | High | Ongoing
81 | WHBC Emissions | Investigate the opportunities for battery storage as a means of shifting demand away from peak times in council owned buildings | Service Manager (b/repairs & C/change) | Medium | Ongoing
82 | Engagement | Develop and implement on and offline mechanisms through which residents, businesses and stakeholders can be involved in the progress and delivery of the CAP. | Corporate Strategy & Engagement Officer | Medium | In progress | Invite comment in ONE magazine (beginning with Summer 2023 edition) and on ONE website
83 | Engagement | Work with partners in education to develop climate education opportunities in schools such as events, workshops, upskilling teachers or activities like school allotments or forest gardens. | Climate Change Officer | Medium | In progress
84 | Engagement | Work with partners to develop climate education opportunities in non-education facilities such as adults in work, adults out of work, carers, seniors and incarcerated people. | Climate Change Officer | Medium | In progress
85 | Engagement | Identify how the training will happen including who will provide the training, the creation of green apprenticeships, partnerships with Local Enterprise Partnerships, SMEs, schools, colleges, universities, job centres etc., upskilling education providers and careers services in identifying future employment trends and opportunities and incentivise re-training. | Climate Change Officer | Medium | In progress
86 | WHBC emissions | Review opportunities to improve levels of insulation in council buildings | Service Manager (b/repairs & C/change) | High | Ongoing
87 | WHBC emissions | Consider the various options for financing the energy efficiency measures identified by the investment grade audits and choose the most appropriate financing option (e.g. self fund, energy performance contract, energy-efficiency-as-a-service, green loan etc) for WHBC | Climate Change Officer | High | Ongoing
88 | WHBC Emissions | Commission a study on how WHBC will decarbonise heat from their building stock e.g. via waste heat recovery, heat networks, district heating, large scale heat pumps, biomass etc. | Service Manager (b/repairs & C/change) | High | In progress
89 | Biodiversity | Maintain up to date management plans for the borough's largest woodlands and open spaces | Landscape and Ecology Manager | Medium | Ongoing | Obtained £245k grant funding for the woodlands
90 | Biodiversity | Work with local volunteer groups to better manage woodlands, trees and open spaces | Landscape and Ecology Manager | Low | Ongoing
91 | Biodiversity | Implement biodiversity net gain policy | Assistant Director (Planning) | High | Ongoing | This work is currently taking place, in conjunction with work being done by HCC through the Hertfordshire LEADS project
92 | Biodiversity | Explore opportunities for additional tree planting around the borough | Landscape and Ecology Manager | High | In progress | Meeting with HCC to discuss funding options
93 | Council Housing | Upgrade communal lighting to LED movement detection lighting in all 560 council housing blocks | Service Manager (Hsg Repairs & B/Safety | High | In progress | EM obtaining prices from contractor to install LED light fittings with motion detectors. Looking at budget reallocation to bring forward a programme for "pilot sites" for 23/24 which will then be monitored for energy reduction.
94 | Transport | Explore the possibility of replacing of general vehicles and community buses with electric vehicles | Service Director (Residents & Neighbourhoods) | High | In progress
95 | Transport | Commission a study to determine the most suitable locations for public EV charge point infrastructure | Parking and Playground Services Manager | Medium | Ongoing
96 | Energy | Help 30 businesses to improve the enery efficiency of their premises through participating in the Eastern New Energy Project | Economic Development Officer | High | In progress | Supported 33 businesses with the project coming to an end. Several businesses are awaiting quotes for work.
97 | Water | Commission a study to investigate ways of reducing water consumption in council buildings | Senior Building Surveyor | Low | In progress
98 | Water | Commission a study to investigate ways of reducing water consumption in council houses | Neighbourhood & Enforcement Manager | Low | Not started
99 | Waste | Review the options for alternative fuels (HVO) to be used in refuse collection and cleansing vehciles used by the council contractor Urbaser | Environment Services Manager | Medium | In progress
100
All actions are measured through SMART targets

## Info
About the action plan | This action plan is a living document and is monitored every 2 months at the Climate Officers Group. Responsibility for maintenance of this action plan sits with the Climate Change Officer, who will keep a Master version. This page provides guidance to those using the action plan. Some of the functionality in this spreadsheet relies on macros, so it is important to enable macros in order for it to work properly.
Master tab | Updates should be made on the 'Master' tab only. This is the only sheet that can be edited. The other sheets are hidden or locked to avoid accidentally overwriting or editing cells. The 'Complete', 'Immediate', 'Short Term', 'Medium Term', and 'Long Term' sheets are different views of the data on the 'Master' tab and are locked.
New Actions | New Actions should be added to the bottom of the list to maintain the reference numbering system in column A of the Master tab. Do not add actions by inserting rows in the middle of the table as this will break the refernce number formula.
Filtering the list for easy completion | To make it easier for multiple people to update the action plan, the list can be filtered by any of the column headings. For example, if you only want to see actions assigned to you, click on the down arrow next to the Heading "Responsible officer", uncheck all the names except your own, then click OK. If you only want to see actions that have been completed, click the down arrow next to the Heading "Status", uncheck all the names except "Complete", then click OK. You can do this for every Heading and can filter on multiple categories to cut the data any way you like. To remove the filters that you have applied click the down arrow again and click "Clear filter from <Heading name>".
Colour codes | Cells in the Status, Level of Control, Carbon reduction impact and Cost columns automatically colour code based on selection using a traffic light syste.
Category | Each action has been assigned to one of the following categories: Funding, Governance, Engagement, WHBC Emissions, Planning, Biodiversity, Transport, Waste, Water, Pollution, Council Housing. When adding actions, please select a category from the drop down list.
Theme/impact area | What area of climate action is being targetted
Action | Give a description of the action. When adding new actions keep in mind the SMART principles, i.e. actions should be Specific, Measurable, Achievable, Realistic and Time-bound. Avoid vague actions where it is unclear whether or not the action has been achieved.
Priority | This describes the approximate time frame for completion of the action: - Immediate: Action is to be completed within the next 12 months. - Short term: Action is to be completed within 1-2 years. - Medium term: Action is to be completed within 3-5 years. - Long term: Action likely to be completed in longer than 5 years. Most actions will be immediate or short term actions but it is useful to have a few longer term goals that are more aspirational and therefore need longer time frames to achieve. Over time, long term actions will become medium term, then short term, then immediate actions.
Due date | Only "Immediate" actions need to have due dates as it's hard to predict completion dates with any accuracy beyond 12 months. There is no need for specific dates. An indication of which quarter the action will be completed in is sufficient e.g. a due date of Q4 2022 means that the action will be completed by 31st December 2022 at the latest. Some actions are recurring e.g. a document that needs to be updated every year. In this case, you can mark the due date as "Continuous" to show that the action repeats periodially.
Completion Date | When the action has been completed, record the completion date. There is no need for specific dates. An indication of which quarter the action was completed in is sufficient e.g. a completion date of Q2 2021 means that the action was completed by 30th June 2021. As for "Due Date", if the action is repeating you can mark this column as "Continuous" after the first instance of the action has occurred.
Action owner | Enter the name of the person who is responsible for making sure this action gets completed or the service area.
Job Title | Enter the Job Title of the Responsible officer in this column. When someone leaves the organisation you can easily see which job function should pick up the action. Plus in published versions of the action plan it keeps some anonymity for local authority officers.
Status | Choose the status of the action from the following options: - Not started (nothing done yet - this is ok, perhaps nothing needs to be done yet) - In progress (done something but there is more to do) - Complete (use this for discrete, finite actions that have definitely been completed and evidence is available to show it has been completed) - Ongoing (use this for actions that have been done but have a due date of "Continuous" to show that the action will reoccur).
Carbon Reduction impact | Choose from one of the following options: - Low (the action does not save any carbon directly but may lead to future carbon savings, or; the action is likely to save less than 1 tonne of carbon per year, or; the action may help others to make savings or be good for the environment in another way). - Medium (the action directly saves between 1 and 25 tonnes of carbon per year, or; the action leads to a large number of people saving a small amount of carbon each) - High (the action directly saves more than 25 tonnes of carbon per year, or: the action leads to a large number of people saving a large amount of carbon each. 25 tonnes has been chosen as the limit for a medium level of carbon savings because this represents 1% of WHBC's 2019/20 baseline carbon footprint.
Action Type | Chose from the following - Tangible - the action is measurable Enabling - the action focuses on a behaviour that is less measurable but will still have a positive impact
Level of control | Choose from one of the following options: - Control (the action is fully within the Council's control, they can make it happen without other stakeholders) - Influence (the action can be partially completed by the Council, but requires cooperation of another stakeholder, or; the Council cannot complete the action tehmselves but can significantly influence the outcome). - Support (the Council can only support the activities of another stakeholder). - Lobby (the Council making its position/opinion known to other stakeholders e.g. National Government, other Associations etc.)
Cost | Choose from one of the following options: - Low <£25k - Medium £25-50k - High £50k+
Net Zero Target | Is the action in relation to council taget of 2030 of boroughwide taget of 2050 or both
Co-benefits | Many actions that are taken to reduce carbon emissions result in other benefits. The main ones are: - Improvements to the health & wellbeing of staff or people who live and wrk in Welwyn Hatfield - Boosts to the local economy e.g. through creating more local jobs, saving people money so they have more disposable income to spend locally etc. - Improvements to the levels of biodiversity in the area through protecting or creating natural habitats - Improvements to social equity by making sure that those most affected by climate change can cope just as easily as those that are less affected - Opportunities to educate & upskill the workforce, the public, people who live and work in the area. - Build resilience to adapt to the impacts of cliamte change Put an x in each column that applies to automatically colour code the actions.
Monitoring | In this column state how you will verify that the action has been completed? What evidence would you show to a third party to show that you have done what you said you would?
'Complete', 'Immediate', 'Short Term', 'Medium Term', and 'Long Term' sheets | The 'Complete', 'Immediate', 'Short Term', 'Medium Term', and 'Long Term' sheets are different views of the data on the 'Master' tab and are locked to avoid accidental overwriting of data. To update these tables, simply click on the button labelled 'Click here to refresh this table'. The buttons use macros so it is important that you enable macros in order for them to work properly. It should not be necessary to edit these sheets in any other way, but in case additional editing is required you can unlock these sheets by going to the 'Review' tab, selecting 'Unprotect Sheet' from the 'Protect' group, then entering the password WelHatCAP.

## Climate Action Plan
Ref | Theme/Impact Area | Action | Action owner | % complete | Status | Carbon reduction impact | Priority | Action type | Level of control | Net Zero target; Council Borough Both | How will this be monitored or evidenced? | Comments | Evidence | Health & Wellbeing | Economy | Biodiversity | Social Equality | Resilience | Education & Skills
1 | Funding | Obtain approval from SLT & CC Member Sub-Group for £150,000 spend on climate change mitigation & adaptation actions for financial years 2020/21, 2021/22 & 2022/23 | Service Manager (b/repairs & C/change) | 100 | Complete | High | High | Enabling | Control | Both | Meeting minutes showing value of budget approved. Breakdown of actions that have been assigned a budget. | To date, £87,840 has been allocated, which leaves £62,160 remaining for future projects. |  | x | x | x | x |  | x
2 | Funding | Determine budget for climate action in future years and obtain approval from SLT | Resident Services and Climate Change | n/a | Ongoing | High | High | Tangible | Control | Both | Meeting minutes showing value of budget approved. Breakdown of actions that have been assigned a budget. | TBC |  | x | x | x | x |  | x
3 | Funding | Carry out a financial mapping exercise to identify opportunities to raise additional funds for decarbonisation projects e.g. what grants or loans are available? | Resident Services and Climate Change | n/a | Ongoing | Low | Medium | Enabling | Control | Both | Financial mapping report has been produced. Opportunities to be pursued have been identified and added to this plan. | Spread sheet started |  |  | x |  | x
4 | Funding | Identify and engage with community groups and other stakeholders who may be able to access funding for decarbonisation projects that is unavailable to local authorities | Climate Change Officer | n/a | Ongoing | Low | Medium | Enabling | Control | Both | List of community groups and other stakeholders that WHBC has engaged with has been produced. Letters/emails/communications with each group are on file. Actions arising from the engagement activity have been added to this plan. |  |  |  | x |  | x
5 | Funding | Seek and promote schemes around the borough such as Home Upgrade Grant (HUG2), Solar together, ECO flex 4/BGIS, BHBH | Climate Change Officer | 10 | In progress | High | High | Tangible | Influence | Borough | Records kept of number and value of grants facilitated and what was funded. Records kept of methods used to promote government grant availability. | Delivery partner not confimed. Can promote once this is declared. Probably mid September |  | x | x |  | x
6 | Governance | Ensure that all committee reports include section on climate change implications | Risk & Resilience Manager | n/a | Complete | Medium | High | Tangible | Control | Both | Check a random sample of committee reports each year. Add corrective actions to this plan if climate change implications were missing, incomplete or inaccurate. |  |  | x | x | x | x |  | x
7 | Governance | Identify joint work programmes with the other district councils in Hertfordshire, Herts County Council and Herts LEP via involvement in the Herts Climate Change and Sustainability Partnership. This includes supporting and aligning with all 6 HCCSP Action Plans (carbon, adaptation, biodiveristy, behavioural change, water, transport) | Climate Change Officer | n/a | Ongoing | High | Medium | Enabling | Influence | Both | List of joint working programmes identified. ^ sub group strategic action plans (Adaptation, behaviour change, biodiversity, carbon ,transport and water) |  |  | x | x | x | x |  | x
8 | Governance | Webcast all committee meetings | Service Manager (b/repairs & C/change) | n/a | Complete | Low | Low | Tangible | Control | N/A | Check webcasts are available here https://welhat.public-i.tv/core/portal/home | This process is now in place so can be marked as complete |  |  |  |  | x |  | x
9 | Engagement | Carry out 6 workshops with local businesses, community groups and landlords on how to effectively support decarbonisation. | Economic Development Officer | 100 | Complete | Medium | Medium | Tangible | Control | Borough | Number of workshops run, dates and attendee lists. Add actions arising from these workshops to this action plan. |  |  |  | x |  |  |  | x
10 | Engagement | Develop a clear communications strategy that includes social media engagement, case study examples, leaflets and posters highlighting the work the council is doing, why it matters and how residents can contribute. Explain impacts of climate change and influence behaviours on a variety of aspects which will lead to positive impacts on climate change. | Communications & Marketing Manger | 20 | In progress | Medium | High | Tangible | Control | Borough | Communication strategy published and reviewed annually. | Comms team are working with the Climate Change Officer on the development of a Climate Change Comms Plan |  |  |  |  | x |  | x
11 | Engagement | Review 'nudge' behaviour theory and use it to identify opportunities to facilitate behaviour change such as publicising walk/cycle to school days. | Climate Change Officer | n/a | Ongoing | Low | Medium | Enabling | Control | Borough | Add actions to this plan relating to use of nudge theory. |  |  | x |  | x
12 | Engagement | Add a 'latest news' feature to the climate change section of the website. Publish a quarterly summary on 'One Welwyn Hatfield' website on achieved climate change action.To include at least 2 social media posts per month | Communications & Marketing Manager | n/a | Ongoing | Low | Medium | Tangible | Control | Borough | Record of number of social media posts and the level of engagement (views/shares/likes) of each one. | Kelly and Rosy will meet after every COG meeting to ensure relevant updates are made online; the two websites and social media platforms | [6 empty] | x
13 | Engagement | Add links to carbon and water footprint calculators that residents can use to calculate their own emissions to council website | Communications & Marketing Manager | 100 | Complete | Low | Medium | Tangible | Control | Borough | Links to carbon calculators available on WHBC website. | Using climate hero to get calculator tool that can aggregate residents footprints and reduction by pledges Will use affinity water for the water footprint | [6 empty] | x
14 | Engagement | Promote public transport, walking and cycling as alternative to driving through public engagement and internally | Communications & Marketing Manager | n/a | Ongoing | Medium | Medium | Enabling | Control | Borough | Record of number of social media posts and the level of engagement (views/shares/likes) of each one. Record of how alternatives to driving were promoted. | promoting Arriva discounted bus tickets to all businesses around the borough |  | x |  |  | x
15 | Engagement | Develop and implement on and offline mechanisms through which residents, businesses and stakeholders can be involved in the progress and delivery of the CAP. | Communications & Marketing Manager | 10 | In progress | Medium | Medium | Tangible | Control | Both | List of on and offline mechanisms and how many people use them. | KM is creating a resident questionaire to gauge interest, current behaviours and resident aspirations for climate action around the borough. Currently sat wth comms to review. To be circulated October(ish). Lso developing the Climate Hub with th ecomms team |  | x | x | x | x |  | x
16 | Engagement | Work with partners in education to develop climate education opportunities in schools such as events, workshops, upskilling teachers or activities like school allotments or forest gardens. | Climate Change Officer | 10 | Ongoing | Medium | Medium | Enabling | Influence | Borough | List of educational activities that took place in schools in last 12 months facilitated or attended by WHBC. | KM Emailed HCC and am setting up primary school session. visiting a school 3rd november |  | x |  | x | x |  | x
17 | Engagement | Work with partners to develop climate education opportunities in non-education facilities such as adults in work, adults out of work, carers and senior people. | Climate Change Officer | 0 | Not started | Medium | Medium | Enabling | Influence | Borough | List of educational activities that took place in on-education settings in last 12 months facilitated or attended by WHBC. | Climate hub will be key to delivering this action. |  | x |  | x | x |  | x
18 | Engagement | Identify how the training will happen including who will provide the training, the creation of green apprenticeships, partnerships with Local Enterprise Partnerships, SMEs, schools, colleges, universities, job centres etc., upskilling education providers and careers services in identifying future employment trends and opportunities and incentivise re-training. | Climate Change Officer | 0 | Not started | Medium | Medium | Enabling | Influence | Borough | Training plans and event agendas. | This is a large piece of owrk and not sure this can progress with current staff capacity and other actions with higher priorities |  |  | x |  | x |  | x
19 | Engagement | Help 30 businesses to improve the energy efficiency of their premises through participating in the Eastern New Energy Project | Economic Development Officer | 100 | Complete | Medium | Medium | Tangible | Influence | Borough | Energy assessment reports for 30 businesses. | Supported 33 businesses with the project. Several businesses are awaiting quotes for work. |  |  | x
20 | Engagement | WENTA programme. To assist up to 100 businesses receving gold standard advice on carbon footprinting and carbon reduction advice. | Economic Development Officer | 5 | In progress | Medium | Medium | Tangible | Support | Borough | Number of businesses sign up will be recorded | Everything signed. Lisa will be promoting in November | [6 empty] | x
21 | Nature and biodiversity | Develop local plan policies that: protect the countryside, open spaces, parks and green spaces; enhances the borough's critical environmental assets; creates and enhances green infrastructure links across the borough; protects and enhances ecological networks and biodiversity assets. | Assistant Director (Planning) | n/a | Ongoing | High | High | Tangible | Control | Both | Local Plan published on WHBC's website | Local plan written 2016, should be approved this year. Will require a short term review to inlcude for cc focused policies |  | x |  | x | x
22 | Nature and biodiversity | Purchase ecological advice from Herts CC to inform Local Plan policies and planning decisions | Assistant Director (Planning) | n/a | Ongoing | Medium | Medium | Tangible | Control | Both | Records of advice received from Herts CC | Entering into SLA eventually |  |  |  | x
23 | Nature and biodiversity | Maintain up-to-date Tree Strategy to guide management of woodlands and street trees | Landscape and Ecology Manager | n/a | Ongoing | Medium | High | Tangible | Control | Both | Tree strategy published on WHBC website. | April 2024 - new strategy |  | x |  | x
24 | Nature and biodiversity | Ensure that tree Officers attend Herts Tree Health Network to learn, monitor, report and take action on pests and diseases related to tree health | Landscape and Ecology Manager | n/a | Ongoing | Low | Medium | Tangible | Control | Both | Meeting minutes from Herts Tree Health Network showing attendee list. | Minimum of two a year |  | x |  | x |  |  | x
25 | Nature and biodiversity | Plant and maintain flowers in key town centre locations | Environment Services Manager | n/a | Ongoing | Low | Low | Tangible | Control | Both | Records of what was planted in town centre location. | Bedding is done twice a year, maintained throughout the year through landscape maintenance contract (continental) |  | x |  | x | x
26 | Nature and biodiversity | Plant and maintain wildflower meadows along key roads | Environment Services Manager | n/a | Ongoing | Low | Low | Tangible | Control | Both | Record of which roads have wildflower areas. | Maintenance ongoing, planting is based on availabiilty/oportunistic and guided by what is in the CMS Green space audit |  | x |  | x | x
27 | Nature and biodiversity | Manage and let WHBC stock of allotment plots | Landscape and Ecology Manager | n/a | Ongoing | Low | Low | Tangible | Control | Both | Record of allotments |  |  | x |  | x | x
28 | Nature and biodiversity | Contribute to HCCSP biodiversity baseline study | Assistant Director (Planning) | 100 | Complete | Low | High | Tangible | Influence | Both | Biodiversity Baseline study published on WHBC website. |  |  |  |  | x
29 | Nature and biodiversity | Contribute to preparation of Herts Green Infrastructure Strategy | Assistant Director (Planning) | 0 | Complete | High | Low | Tangible | Influence | Both | Herts Green Infrastructure Strategy published on WHBC website (2011) | Is uploaded |  |  |  | x
30 | Nature and biodiversity | Plant 300 street trees (of appropriate species and in appropriate locations) per year until WHBC | Landscape and Ecology Manager | 100 | Complete | Medium | Medium | Tangible | Control | Both | Record of number of street trees planted per year, number removed and total number. |  |  | x |  | x | x
31 | Nature and biodiversity | Explore merits of purchasing of land for new tree planting on land not owned by council for enhanced tree planting | Estates and Landscape and Ecology Manager | 0 | Not started | High | High | Tangible | Control | Both | Record of investigation and any purchased land | Olly to confirm locations, Geoff to review and evaluate. Currently no resource in house to value property. SLT would need to decide if we need to buy third party sites
32 | Nature and biodiversity | Maintain up to date management plans for the borough's largest woodlands and open spaces | Landscape and Ecology Manager | n/a | Ongoing | Medium | Medium | Tangible | Control | Both | Woodland Management Plan published | Obtained £245k grant funding for the woodlands |  | x |  | x
33 | Nature and biodiversity | Work with local volunteer groups to better manage woodlands, trees, and open spaces | Landscape and Ecology Manager | n/a | Ongoing | Low | Low | Enabling | Influence | Both | Records of engagement with local volunteer groups. |  |  | x |  | x |  |  | x
34 | Nature and biodiversity | Implement biodiversity net gain policy | Assistant Director (Planning) | 20 | On going | High | High | Tangible | Control | Both | Biodiversity net gain policy published. | This work is currently taking place, in conjunction with work being done by HCC through the Hertfordshire LEADS project. Pushed back to January (Central gov) . Policy in local pan (adopted last week) . Guidance note on how this will be enforced (approved in August |  |  |  | x
35 | Nature and biodiversity | Explore opportunities for additional tree planting around the borough | Landscape and Ecology Manager | 30 | In progress | High | Medium | Enabling | Control | Both | List of opportunities for tree planting around the borough. Record of participants in the Your Tree Our Future Initiative | Green space audit CMS identified areas for general biodiversity improvement. Facilitated through Your Tree Our Future Initiative |  | x |  | x
36 | Nature and biodiversity | Where possible, increase existing tree canopy cover in wards with lower levels of canopy cover (below 15%) | Landscape and Ecology Manager |  | On going | Medium |  | Tangible | Control | Both | Record of canopy cover percentage |  |  | x |  | x
37 | Planning | Develop local plan policies that support sustainable design and construction principles | Assistant Director (Planning) | 100 | Complete | Medium | High | Tangible | Control | Both | Local Plan published on WHBC website. | In review |  | x | x | x | x |  | x
38 | Planning | Develop local plan policies that support the achievement of BREEAM Excellent standard for new non-residential buildings | Assistant Director (Planning) | 100 | Complete | Medium | High | Tangible | Control | Borough | Local plan policies on WHBC website. | In review |  | x |  | x
39 | Planning | Carry out a sustainability appraisal and habitats assessment of the submitted local plan. | Assistant Director (Planning) | 100 | Complete | Medium | High | Tangible | Control | Both | Sustainability appraisal complete. Recommendations from the report implemented or added to this plan. | In review |  |  |  | x
40 | Planning | Carry out a viability assessment of the policies in in the local plan to ensure that they are not prohibitively expensive for developers | Assistant Director (Planning) | 100 | Complete | Low | High | Tangible | Control | Borough | Viability assessment complete. Recommendations from the assessment implemented or added to this plan. | In review |  |  | x |  |  |  | x
41 | Planning | Creation of a sustainability SPD - To ensure that all future planning applications are scrutinised and encouraged to go beyond minimum standards to improve their long term sustainability, reduce embodied and operational carbon footprint and increase resilience to the impacts of climate change. | Assistant Director (Planning) | n/a | Ongoing | High | High | Tangible | Control | Both | Planning records that show developers being required to go beyond minimum standards. | This takes place on an application by application basis, and subject to appropriate policy requirements. Hertfordshire Growth Board is producing a Developer Charter and seeking developers to support this. This would commit developers to delivering above Building standards in these areas. |  | x | x | x | x |  | x
42 | Planning | Develop Local Plan policies that prevent development from having unacceptable impacts on the environment and human health | Assistant Director (Planning) | 100 | Complete | Medium | High | Tangible | Control | Borough | Local Plan published on WHBC website. | In review |  | x | x | x | x |  | x
43 | Transport | Continue to work with Herts County Council to implement policies in Local Transport Plan and other transport plans | Assistant Director (Planning) | n/a | Ongoing | Medium | Low | Enabling | Influence | Borough | Records of meetings with HCC. |  |  | x | x |  | x
44 | Transport | Ensure Local Plan policies include provision for pedestrians, cyclists, public transport and electric vehicles | Assistant Director (Planning) | 100 | Complete | Medium | High | Tangible | Control | Borough | Local Plan published on WHBC website. | In review |  | x | x |  | x
45 | Transport | Conduct a new staff travel survey and produce an up-to-date Sustainable Travel Plan, and moving forward it should be updated every three years. | Climate Change Officer | 5 | Complete | Low | Medium | Tangible | Control | Council | Green Travel Plan published on WHBC website. | https://welhat.sharepoint.com/sites/intranet/our-council/Shared%20Documents/Climate%20Change/Campus%20East%20and%20West%20Travel%20Plan.pdf?csf=1&web=1&e=aVb768 | Travel survey to be circulated w/c 25th Sept | x |  |  | x
46 | Transport | Support the A414 Group to investigate the merits of mass rapid transit options | Assistant Director (Planning) | n/a | Complete | Medium | Low | Enabling | Support | Borough | Record of communications with A414 group. |  |  | x | x |  | x
47 | Transport | Support the Intalink Partnership to encourage greater bus patronage | Senior Projects Officer (Planning) | n/a | Complete | Medium | Low | Enabling | Support | Borough | Record of comunications wit h Intalink Partnership. Records of activities to promote greater bus patronage. | Look into this one as potentially removing |  | x | x |  | x
48 | Transport | Apply for and implement Government funding programmes for on and off street electric vehicle charge points as and when funding is available | Parking and Playground Services Manager and Climate change officer | n/a | Ongoing | Medium | Medium | Tangible | Control | Both | Application submited. | Funding has been applied for and granted. Install programme in progress. |  |  | x |  | x
49 | Transport | Support the Living Lab project to trial electric and driverless vehicles in Hatfield business park | Senior Projects Officer (Planning) | n/a | Ongoing | Low | Low | Enabling | Support | Borough | Report detailing the findings of the trial. | NO direct control |  |  | x |  |  |  | x
50 | Transport | Review car parking charges as part of budget setting process with a view to generating a budget to invest in new green transport options. | Parking and Playground Services Manager | 100 | Complete | Low | Low | Enabling | Control | Borough | Estimate of budget that could be generated from car parking charges. |  |  |  | x |  | x
51 | Transport | Work with Herts County Council to prepare Walking and Cycling Improvement Plan for Welwyn Garden City and Hatfield | Senior Projects Officer (Planning) | 100 | Complete | Medium | Medium | Enabling | Control | Borough | Walking and Cycling Improvement Plan Published. Any actions identified are added to this plan | Being provided bike maintenance stands and £2k for Dr Bike sessions as part of LCWIP funding BC HCCSP subgroup will help promote this |  | x | x |  | x
52 | Transport | Approve and publish Local Plan and Local Transport Plan policies that facilitate a significant uptake in cycling by improving safety, travel routes and storage facilities. | Senior Projects Officer (Planning) |  | In progress | Medium | Medium | Tangible | Control | Borough | Local Plan and Local Transport Plan published. | Alban Way cycle route maintenance and improvement |  | x |  |  | x
53 | Transport | Explore the possibility of replacing general vehicles with electric vehicles (community buses now contracted out to 'Communities first') | Service Director (Residents & Neighbourhoods) |  | In progress | High | High | Tangible | Control | Borough | Options appriasal evaluating the options for electric vehicles and buses. |  |  | x | x
54 | Transport | Commission a study to determine the most suitable locations for public EV charge point infrastructure | Parking and Playground Services Manager | 5 | In progress | Medium | Medium | Tangible | Control | Borough | Report on EV charging locations published. | Attended EV mapping tool session for 30th August. Have access to software to locate locations |  |  | x |  | x
55 | Transport | Transition owned and operated fleet vehicles to electric by 2030 where financially viable | Executive Director (Finance & Transformation) |  | Not started | Medium |  | Tangible | Control | Council | Record of owned and operated fleet. |  |  | x | x
56 | Energy - domestic | Make it council policy to take a 'fabric first' approach to council house retrofit | Service Manager (Investment P/Delivery) | 100 | Complete | High | Medium | Tangible | Control | Both | Council policy on fabric first approach published on WHBC website. |  |  | x | x |  | x
57 | Energy - domestic | Review opportunities to improve levels of insulation in council buildings | Service Manager (b/repairs & C/change) | n/a | Ongoing | High | Medium | Tangible | Control | Both | List of insulation opportunities produced. |  |  | x | x
58 | Energy - domestic | Bid to Government's Green Homes Grant to improve EPC rating of 32 council houses | Housing | 100 | Complete | Medium | Medium | Tangible | Control | Borough | Bid submitted. |  |  |  | x |  | x
59 | Energy - domestic | Commission a study to investigate the magnitude of carbon emissions from council housing stock | Climate Change Officer | 0 | Not started | High | Medium | Tangible | Control | Both | Results of the study published. Recommendations from the study added to this plan as actions. | This will be completed following the completion of the 1 year stock condition surveys and EPCs by 31/03/24. The EPC surveys will assist in calculating the baseline figure (november) |  |  | x
60 | Energy - domestic | Ludwick Way & Commons - 10 family homes, air source heat pumps, solar panels , water saving systems e.g toilet cistern , fabric first approach , EV charging points | Housing & Development Strategy Services Manager | 100 | Complete | Medium | Medium | Tangible | Control | Borough | Development built | Been delivered Marshall close. Suggested occupant survey . Electric Blue EV charge point. EV Car share scheme (Enterprise )
61 | Energy - domestic | Howlands House and Burfield Close temporary accommodation schemes , 116 homes , which will include , air source heat pumps , solar panels, water saving devices , fabric first approach , mechanical ventilation and heat recovery , EV car sharing points | Housing & Development Strategy Services Manager |  | In progress | Medium | High | Tangible | Control | Borough | Development built | Burfield Close – is at present not progressing , so its only Howlands
62 | Energy - domestic | Review of all financial appraisals for the inclusion of green technologies in all new builds | Housing & Development Strategy Services Manager | 100 | Complete | Medium | Medium | Tangible | Control | Both | Record of financial appraisals
63 | Energy - domestic | Include Climate Change agenda in the affordable homes design brief and set out design standards including Future Homes Standard and incorporating uplift in Building Regulations | Housing & Development Strategy Services Manager | 60 | In progress | Medium | Medium | Tangible | Control | Both | Affordable Homes Design Brief | The design brief I am updating at present it and will go out to consultation with internal colleagues , members and tenants panels in the next few weeks so 60 % written , so will be shared with the climate change group |  | Health & Wellbeing |  |  | x
64 | Energy - domestic | Stock condition surveys Develop a programme of retrofit assessments across housing stock which will help identify decarbonisation and energy efficiency measures required on our lowest performing homes. | Building Serivces Manager |  | In progress | High | High | Tangible | Control | Both | The survey being used by the contractor will be compliant with our asset management system (MRI) and the data will be inputted into this. Savills will meet with WHBC during the process on a regular basis to review progress and analyse the data. Also, any photos or attachments will be stored in our document management system. | This will be completed following the completion of the 1 year stock condition surveys and EPCs . Surveys commence Jan 2024
65 | Energy - domestic | Retrofit programme (SHDF) Implement the energy efficiency measures identified by the investment grade energy audits of council owned social housing (in action 64) | Project manager (SHDF) | 0 | In progress | High | High | Tangible | Control | Both | All documents are stored on a SharePoint. When contractor submits application for payments, they also zip the relevant documents to support their claim. For auditing purposes all actual jobs such as windows and doors/roofs/EWI are raised on orchard which will have its own unique reference job number | Works have already begun and 20/186 properties have had works completed
66 | Energy - domestic | Upgrade communal lighting to LED movement detection lighting in all 560 council housing blocks | Repairs service manager | 10 | In progress | High | High | Tangible | Control | Both | Records of number of council housing blocks with LED movement detection in communal areas. | Funding has been approved for 50 blocks. To commence Autumn 2023. First block will be 101-117 BROADWATER CRESENT . LED and motion sensors |  |  | x |  | x
67 | Energy - domestic | Work with private landlords to implement Minimum Energy Efficiency Standards (MEES) | Housing & Development Strategy Services Manager |  | Not started | Medium |  | Tangible | Control | Borough | Record of investigations and enforcements |  |  | x
68 | Water | Ensure that Local Plan policies state that new homes must achieve water consumption of 110 litres per person per day | Assistant Director (Planning) | 100 | Complete | Low | Medium | Tangible | Control | Both | Local Plan published on WHBC website. | In review |  |  | x |  | x
69 | Water | Ensure that Local Plan policies state that development should consider flood risk and surface water management | Assistant Director (Planning) | 100 | Complete | Low | Low | Tangible | Control | N/A | Local Plan published on WHBC website. | In review |  | x | x | x | x
70 | Water | Commission a study to investigate ways of reducing water consumption in council owned and operated commercial buildings | Senior Building Surveyor | 0 | Complete | Low | Medium | Tangible | Control | Council | Monthly water meter readings show decline in consumption over time. | MC- A review has been carried out on operational buildings with water saving measures in place |  |  | x
71 | Water | Implement actions to reduce water consumption in council owned and operated commercial buildings based on the outcome of the investigation | Senior Building Surveyor | 0 | Complete | Low | Low | Tangible | Control | Council | Report on the results of the study published. Recommendations from the study added to this plan as actions. | MC- A review has been carried out on operational buildings with water saving measures in place |  |  | x
72 | Water | Work with partners to install water saving devices into social and privately owned homes | Neighbourhood & Enforcement Manager |  | Ongoing | Low | Low | Tangible | Control | Borough | Affinity water to provide reports and building maintenance teams to record data | This is being picked up again with Affinity Water |  |  | x
73 | Waste | Examine data from North and East Herts District Councils' consultation with residents on residual waste collection and use it to inform WHBC's decision on moving to less frequent collections at the end of the current waste contract | Environment Services Manager |  | In progress | Low | Low | Enabling | Control | Borough | Data from the North & East Herts consultation obtained | We can relook at this in 3 -4 years year. Government say we need to collect bi weekly (residual minimum bi weekely ) CHange to congoing as it is paused |  |  | x |  | x
74 | Waste | Ensure that guidance on household waste collections is available and clearly signposted on WHBC website | Environment Services Manager | 100 | Complete | Medium | Medium | Tangible | Control | Borough | Details are available on the website. Number of contaminated bins reduces over time. |  |  |  |  | x |  |  | x
75 | Waste | Install recycling bins throughout council offices | Senior Building Surveyor | 100 | Complete | Low | Low | Tangible | Control | Council | Record of number of bins installed. Waste audit showing number of bins contaminated with incorrect materials. | Need to follow up how this is then disposed of as it is belived it all gets collected for landfill. Check with building services on which contractor we use for campus east. Any business with more than 10FTE's by April 1st 2025 all waste streams will need to seperated out. Needs to be made into a new action, as this will is newly mandated by central government (dry mix, food, and residual) |  |  | x
76 | Waste | Phase out the use of disposable cups in council facilities | Senior Building Surveyor | 50 | In progress | Low | Low | Tangible | Control | Council | Regular check in food and drink outlets for single use items. | Revisit this - John Beare |  |  | x
77 | Waste | Ensure that councillors use tablets and officers use laptops for all council meetings rather than printed papers | Governance Services Manager | 100 | Complete | Low | Low | Tangible | Control | Council | Self monitored |  |  |  | x
78 | Waste | Ensure that council target to recycle 53% of household waste is being met for 2024/25 | Environment Services Manager | n/a | Ongoing | Medium | Medium | Tangible | Influence | Borough | Carry out a waste audit to measure recycling rate. | Q1 was 52%, Q2 Provisional 51.6% |  |  | x | x
79 | Waste | Support Herts Waste Partnership Waste Aware Group by promoting its campaigns | Environment Services Manager | n/a | Ongoing | Low | Medium | Tangible | Support | Borough | Record of communications with Herts Waste Partnership. |  |  |  | x | x
80 | Waste | Attend 6 events per year at schools and other educational providers to promote WHBC waste initiatives | Environment Services Manager | n/a | Ongoing | Medium | Medium | Tangible | Control | Borough | Record of number of events attended, list of topics covered, number of attendees. |  |  |  |  | x
81 | Waste | Review Increasing the recycling rate of the borough to at least 55% by 2026 and achieve the government target of 65% by 2036. | Environment Services Manager | n/a | Ongoing | Low | Low | Enabling | Control | Borough | Meeting minutes where the issue was discussed. Report on whether 55% target is achievable/cost to implement. |  |  |  | x | x
82 | Waste | Review the options for alternative fuels (HVO) to be used in refuse collection and cleansing vehicles used by the council contractor Urbaser | Environment Services Manager | 30 | In progress | Medium | High | Tangible | Control | Borough | Proposal to COG on option for trial with associated costs. | Requested cost model from Urbaser for 3 month trial on 3 x vehicles. Once received will consider funding options. We will have to fund price per litre etc maybe opportunity with HCC as they co-occupy the site. 4 more years on the contract - vehicles will be end of life around that itme anyway so will look to electrify then. There are two EV chargepoints thre and infrastructre for 6 EV points (FCC environmental about October ) |  |  | x
83 | Waste | Install adequate bins to facilitate the separation of all waste streams (dry mix, food, residual) in commercial portfolio. | Environment Services Manager and building services |  | Not started | Medium |  | Tangible | Control | Council | Bins will be installed
84 | Energy - commercial | Ensure that New Hatfield Commons multi-storey car park includes low energy features and 8 electric vehicle charge points | Development Manager | 100 | Complete | High | High | Tangible | Control | Both | Low energy features successfully installed. 8 electric charge points installed. Compare car park energy consumtion to benchmarks of other car parks to check if it is operating efficiently as expected. |  |  |  | x
85 | Energy - commercial | Bid into Public Sector Decarbonisation Scheme 1 to replace gas boilers with air/water source heat pumps and install solar panels at Campus East, Campus West and Hatfield Swim Centre to reduce the carbon footprint. | Service Manager (b/repairs & C/change) | 100 | Complete | High | High | Tangible | Control | Council | Proposal written and submitted to PSDS. |  |  |  | x |  |  |  | x
86 | Energy - commercial | Energy audits of council owned commercial buildings and development of work plan to make improvements according to findings in line with MEES | Service Manager (b/repairs & C/change) | 10 | Ongoing | High | High | Tangible | Control | Council | Energy bills pre and post intervention for council buildings. | Some builgings done (Campus East) |  | x | x
87 | Energy - commercial | Investigate the opportunities for battery storage as a means of shifting demand away from peak times in council owned buildings | Service Manager (b/repairs & C/change) | 0 | Not started | Medium | Medium | Tangible | Control | Council | Summary report of opportunities for load shifting through use of batteries. | Due to current budgetary constraints this is currently on hold |  |  | x
88 | Energy - commercial | Consider the various options for financing the energy efficiency measures identified by the investment grade audits and choose the most appropriate financing option (e.g. self-fund, energy performance contract, energy-efficiency-as-a-service, green loan etc) for WHBC | Climate Change Officer | n/a | Ongoing | High | Medium | Tangible | Control | Council | Report on financing options for energy efficiency measures. |  |  | x | x |  |  |  | x
89 | Energy - commercial | Commission a study on how WHBC will decarbonise heat from their building stock e.g. via waste heat recovery, heat networks, district heating, large scale heat pumps, biomass etc. | Service Manager (b/repairs & C/change) |  | In progress | High | High | Enabling | Control | Council | Report on how WHBC can decarbonise heat from their building stock. |  |  |  | x |  | x |  | x
90 | Energy - commercial | Implement an environmental management system (ISO 50001) | Service Manager (b/repairs & C/change) | 20 | In progress | High | Medium | Tangible | Control | Council | Environemtal management system will be adopted |  |  | x
91 | Internal | Calculate the council's own carbon emissions (Scopes 1, 2, and 3) at least annually to check if emissions are being reduced Calculate borough wide emissions | Climate Change Officer | n/a | Ongoing | Low | High | Tangible | Control | Council | Breakdown of council's own carbon emissions available for each financial year. | 2022/23 underway to be completed next month by Team Energy Borough wide complete |  |  | x
92 | Internal | Investigate the most suitable carbon removal offsetting options | Climate Change Officer | n/a | Ongoing | Low | High | Tangible | Control | Both | Options appriasal covering the carbon removal offset options. |  |  |  | x | x
93 | Internal | Implement agile working arrangements for most WHBC staff | Executive Director (Finance & Transformation) | 100 | Complete | Medium | High | Tangible | Control | Council | Agile working policy. Records of office/desk utilisation rates. |  |  | x | x |  | x
94 | Internal | Promote internal sustainable behaviour; push green staff incentives, use of EV and e pool bikes and add sustainability chapter in teams’ charters, staff sustainability champion | Climate Change Officer and Communications Team | n/a | Ongoing | Low | Low | Tangible | Influence | Council | Energy assessment reports for 30 businesses. |  |  |  | x
95 | Internal | Provide carbon literacy training for all councillors | Climate Change Officer | 10 | In progress | Low | Medium | Tangible | Control | Council | Record of training, date and attendee list. | LGA tool and HCCSP video circulated |  | x | x | x | x |  | x
96 | Internal | Roll out carbon literacy training to all local authority staff (minimum FTE 50%) | Climate Change Officer | 0 | Not started | Medium | Medium | Tangible | Control | Council | Record of training, date and attendee list. | Mandatory training is being prioritised and HR will be in touch in the new year to discuss training available on WINNIE.Once they are ready to start the development work we will see what is the best way to deliver courses. That could be building our own, or using existing e-learning options if suitable. | Factor in length of course and feasibility of this. Minimum FTE 50% | x | x | x | x |  | x
97 | Internal | Create a Climate Change Strategy / Transistion to Net Zero Document | Climate Change Officer | 10 | Complete | Low | Medium | Tangible | Control | Both | Published strategy document - but updating to be more visually pleasing | Based on existing strategy |  | x | x | x | x |  | x
98 | Procurement | Develop a Sustainable Procurement Strategy that ensures that social, economic, environmental and climate change issues are considered in all procurements, and assesses suppliers carbon management and reporting practises | Procurement Manager | 100 | Complete | Medium | High | Tangible | Control | Council | Sustaianble procurement strategy will be published on WHBC website. Check a random sample of tender 5 documents each year to ensure that they included sustainability and carbon reduction requirements. Add corrective actions to this plan if requirements were not included. | Procurement strategy 2021-2025 exisitng - but expanding |  |  | x | x | x
99 | Procurement | Include sustainability and carbon reduction requirements as part of the assessment criteria for all procurements | Procurement Manager | n/a | Ongoing | Medium | High | Tangible | Control | Council | Check a random sample of tender 5 documents each year to ensure that they included sustainability and carbon reduction requirements. Add corrective actions to this plan if requirements were not included. | Contracts procedure rules - updated June 2023 |  |  | x | x | x
100 | Air quality | Meet national air quality objectives and air quality standards regulation Monitor AQ around the borough and engage with residents around AQ issues | Env Health Technical Officer |  | In progress | Low | Low | Tangible | Control | Both | Record of survey questions and responses. Actions arising from review of the survey results to be added to this plan. | Annual monitoring report in review. Action plan in review |  | x | x | x | x |  | x
101 | Governance | Publish Climate Change Risk Assessment assessing in detail anticipated local impacts (heat, drought, flooding etc) to understand what adaptation measures are needed. | Climate Change Officer | 30 | Complete | Low | High | Tangible | Control | N/A | Climate Change Risk Assessment published on WHBC website | We need to complete this by December 2023
102 | Adaptation | Ensure climate change risks identified in the CCRA are monitored within current risk management process and develop mechanism to ensure actions designed to build climate resilience can progress | Health & Safety and Resilience Manager and Climate Change Officer |  | Ongoing | Low |  | Tangible | Influence | Both | Climate change risks added to corporate and operational risk registers and monitored interally
All actions are measured through SMART targets
Note on M13: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can this be combined with 14?

## HCCSP actions to be incorporate (hidden)
This will be updated early next year once all the sub groups have released their new and updated action plans

## Actions for review (hidden)
Ref | Category | Action | Job Title | Carbon reduction impact | Status | Comments
1 | Funding | Identify potential revenue generating council activity, such as demand parking charges or equity investors that can be used to raise funds for decarbonisation projects | Parking & Playground Services Manager | Low | Not started | Geoff
2 | Governance | Use position as an active member of the Recycling Advisory Committee to lobby DEFRA on improving the national waste strategy and national targets for recycling rates | Service Director (Residents & Neighbourhoods) | Low | Ongoing
3 | Governance | Commission a study to understand the magnitude of WHBC's Scope 3 emissions | Climate Change Officer | Low | Not started | Can investigate primary data sources for the following. Obviously any of these emission sources that get reported will need to be reduced and offset. Staff commuting Well to Tank Rented areas in social housing and leased commercial buildings Supply chain/procurement Embodied carbon in new builds Water and waste water in commercial buildings Home working
4 | Governance | Commission a study to understand the borough wide carbon baseline, carbon trajectory and likely level of impact of this CAP. | Climate Change Officer | Low | Not started | Boroughwide carbon baseline completed along with trajectory. Level of impact of this CAP - not completed... will be challenging but can investigate
5 | Engagement | Facilitate workshops with local partners and stakeholders to identify collaborative opportunities and barriers to decarbonisation. | Climate Change Officer | Low | Not started | This is part of the climate hub
6 | Engagement | Undertake bi annual community consultation exercise to determine which issues are of most importance to the public and gather their ideas on carbon reduction activities | Climate Change Officer | Low | Not started | This is being done - resident survey being released this week
7 | Engagement | Provide seed funding and business case support for 10 community and social enterprises wishing to invest in circular economy, renewable energy generation, upskilling and other initiatives that support economic development & WHBC's social & environmental goals. | Economic Development Officer | Medium | Not started | Lisa
8 | Engagement | Map local organsations that have their own net zero objectives. | Climate Change Officer | Low | Not started | This is part of the climate hub
9 | Engagement | Carry out a feasibility study to assess the benefits of setting up a coalition of external stakeholders, including under-represented groups, who can contribute to future climate action planning | Climate Change Officer | Low | Not started | This is part of the climate hub
10 | Engagement | Train all officers that are involved in procurement activities on assessing social, environmental and economic impacts of spending and how to maximise benefits from Social Value Act 2012. | Procurement Manager | Medium | Started | Andrew
11 | WHBC emissions | Move electricity supply for WHBC and Leisure Centre buildings to a green tariff | Service Manager (b/repairs & C/change) | Low | Not started | Mark
12 | Planning | Respond to Government consultations to support the setting and achievement of higher climate change standards | Assistant Director (Planning) | Low | Not started | Chris
13 | Energy | Support the Greater South East Energy Hub and other external partners to develop low-carbon economy | Service Manager (b/repairs & C/change) | Medium | Not started | Already partnering with HUG2 and eco flex4 and GBIS
14 | Energy | Decide whether to remove the need to seek planning permission for installing solar panels and sustainability features on WGC EMS homes | Assistant Director (Planning) | Medium | Not started | Chris
15 | Transport | Investigate with delivery companies and Royal Mail clean freight initiatives alternatives, such as: cargobikes to reduce emissions, congestion and improve air quality; an edge-of-town delivery hub to reduce vans and lorries polluting and congesting town centres etc. | Climate Change Officer | High | Not started | Current staff capcaity constraints tp progress this
16 | Governance | Include environmental and energy efficiency metrics in KPIs and departmental targets of all WHBC departments. | Directors/Assistant Directors | High | Not started | This is included in ISO 50001
18 | Governance | Carry out an Equalities Impact Assessment to ensure all residents, demographically and geographically, are fairly benefiting (and not adversely impacted) by CAP policies. | Head of Community & Housing Strategy | Low | Not started | Joyce
19 | Engagement | Develop a plan for implementing the ideas resulting from the workshops, consultations and engagement activities described in this plan | Climate Change Officer | Low | Not started | Current staff capcaity constraints tp progress this
20 | Engagement | Identify gaps in current partnerships (e.g. do partnerships exist with voluntary, education, health, farming, industry, high emitting sectors, faith organisations, anchor institutions and businesses. | Climate Change Officer | Low | Not started | This is part of the climate hub
21 | Engagement | If gaps were found in current partnerships, work to establish links with those communities. | Climate Change Officer | Low | Not started | This is part of the climate hub
22 | Engagement | Explore opportunities to co-design spaces (for example, local children and the design of a new park) to empower residents. |  | Low | Not started
23 | WHBC Emissions | Develop a policy on green roofs, walls and canopies to mitigate potential flooding, heat island and biodiversity risks by taking advantage of non-traditional locations for planting, (this should be complementary to the existing 'tiny forests' policy) | Case Officer | Low | Not started | Olly/Chris
24 | Planning | Develop Masterplans for strategic development sites that put WHBC's climate change aspirations at their core | Assistant Director (Planning) | Medium | Not started | Chris
25 | Biodiversity | Consider opportunities to plant 'tiny forests' in urban areas | Landscape and Ecology Manager | Medium | Not started | Olly
26 | Biodiversity | Develop a food, soil and carbon sequestration stategy to support the decarbonisation efforts of local producers and maximise the carbon sequestration potential of green spaces. | Case Officer | Medium | Not started | Olly??
27 | Transport | Install bike lockers, racks and hangers at public locations, such as train & bus stops, shopping centres, residential and office developments as well as car parks and appropriate streets. | Senior Projects Officer (Planning) | Low | Not started | Matt Pyecorft?
28 | Waste | Work with local businesses and communities to reduce packaging, increase sharing/circular economies (such as hosting or publicising freecycle events or forums), discouraging food waste and driving behaviour change. | Economic Development Officer | Medium | Not started | Lisa
29 | Engagement | Work with and support local community groups to apply for funding that is unavailable to the council (e.g. for energy efficiency upgrades, training etc) | Climate Change Officer | Medium | Not started | This is part of the climate hub
| Council Housing | Pilot scheme has been carried out on 2 housing properties where ASHPs have been installed with subsequent Megaflow installs and monitoring of energy consumption is now taking place

## New actions (hidden)
Theme | Action | Time frame | Status
Internal | Implement an environmental management system (ISO 15001) |  | Added to CAP
Internal | Promote internal sustainable behaviour; push green staff incentives, use of EV and e pool bikes and add sustainability chapter in teams’ charters, staff sustainability champion |  | Added to CAP
Transport | Transition owned and operated fleet vehicles to eklectric by 2030 where financially viable | 2030 | HCCSP transport plan action - "All local authorities to have adopted a plan to have a zero-emissions vehicle fleet by 2030, with the exception of HGVs and other specialised or customised vehicles."
Transport | Explore the use of e bikes for building surveyors |  | To be explored
Internal | Compliance with commercial MEES | 2027 | Will depend on stock condition survey. but is mandatory so should be included
Internal | Replace all WHBC owned street lighting with LED's |  | Need to explore
Biodiversity | Biodiversity Duty - January |  | Added to CAP
Engagement | WENTA programme |  | Added to CAP
Procurement | Create a sustainable procurement strategy |  | Added to CAP
Waste | A 10% reduction in residual waste per household waste from 2023/24 (400kg per houseghold) | 2030 | Will discuss at COG
Waste | Install adequate bins to facilitate the seperation of all waste streams (dry mix, food, residual) in commercial portfolio - this is mandated by central government by 1.4.25) | 2025 | Will discuss at COG
Air Quality | Borough to meet national Air Quality Objectives and Air Quality Standards Regulation | Ongoing | Will discuss at COG
Biodiversity | Where possible increase existing tree canopy in wards with lower levels of canopy cover (below 15%) | 2030 | Will discuss at COG
Biodiversity | Minimise the use of pesticides/herbicides | 2030 | Will discuss at COG
Biodiversity | 30% by area of our green spaces managed to support nature by 2030 | 2030 | Will discuss at COG
Adaptation | Ensure actions identified in CCRA are updated in business continuity plans where possible | Ongoing | Will discuss at COG
Adaptation | Introduce training for Development Management and those associated with capital projects team on resilience and adpatation. | HCCSP | Will discuss at COG
Adaptation | Develop an Extreme Weather Plan for both hot and cold weather scenarios | 2025 | Will discuss at COG
Adaptation | Create a register for buildings at risk of sever weather events | 2025 | Will discuss at COG
Adaptation | Create an extreme weather incident log | Ongoing | Will discuss at COG
Adaptation | From stock condition survey, look to improve ventilation where possible in conjunction with retrofit work and planned maintenance/repairs/voids | 2030 | Will discuss at COG
Adaptation | Develop comms plan for weather warning/alerts and advice | HCCSP | Will discuss at COG
Adaptation | Consider feasibility of increasing shading, ventilation or cooling equipment in commercial buildings | No building service manager to confirm | Will discuss at COG
Adaptation | Consider developing outside respite areas (increased shade and water availability) through increased tree planting in open areas and along paths. | Ongoing | Will discuss at COG
Adaptation | Map areas of potential high impact with potential for major solar gain, ie pre 1960's housing. | HCCSP | Will discuss at COG
Adaptation | Consideration of measures such as rainwater harvesting, grey water recycling and measures to reduce household water demand and use in social housing (e.g., through installation of water efficiency measures) |  | Will discuss at COG
Adaptation | Investigate feasibility of installing green rooves on homes, bin stores, bikes sheds etc | HCCSP | Will discuss at COG
Adaptation | Continued engagement and external stakeholders such as LLFA, FIre and rescue etc | HCCSP | Will discuss at COG
Adaptation | Engage with stakeholders to dicsuss WHBC impact on river flow and water management and discuss possible mitigation measures on our land. | HCCSP | Will discuss at COG
Adaptation | Explore additional offsetting solutions to sequester carbon to offset any unabated emissions in order to acheive our net zero target. | 2030 | Will discuss at COG
Adaptation | Investigate the cost of purchasing heat maps to identify hot spots | HCCSP | Will discuss at COG
Adaptation | Mapping exercise to identify vulnerable areas (based on heat island, LSOA etc) | HCCSP | Will discuss at COG
Energy - domestic | The Domestic Minimum Energy Efficiency Standard (MEES) Regulations set a minimum energy efficiency level for domestic private rented properties an EPC rating of E at the least

## Analysis (hidden)
Action Status | Number of actions | Percentage | Theme/Impact area | Number of actions
Completed | 36 | 36 | Funding | 5
On going | 35 | 35 | Governance | 6
In progress | 23 | 23 | Engagement | 12
Not started | 6 | 6 | Biodiversity | 15
Total | 100 | 100 | Planning | 6
|  |  | Transport | 12
|  |  | Energy - domestic | 11
|  |  | Water | 5
|  |  | Waste | 10
|  |  | Energy - commercial | 7
|  |  | Internal | 7
|  |  | Procurement | 2
|  |  | Air quality | 1
|  |  | HCCSP | 1
|  |  | Total | 100

## Adaptation (hidden)
100 | Adaptation | Ensure actions identified in CCRA are updated in business continuity plans where possible | Risk leads |  | In business continuity plans
101 | Adaptation | Introduce training for Development Management and those associated with capital projects team on resilience and adpatation. | HR | 50 |  | Cold weather completed. Hot weather not commenced
102 | Adaptation | Develop an Extreme Weather Plan for both hot and cold weather scenarios | Service Director (Residents & Neighbourhoods) |  | Extreme Weather Plan is published on WHBC's website.
103 | Adaptation | Create a register for buildings at risk of sever weather events | Building services manager
104 | Adaptation | Create an extreme weather incident log | Service Director (Residents & Neighbourhoods)
105 | Adaptation | From stock condition survey, look to improve ventilation where possible in conjunction with retrofit work and planned maintenance/repairs/voids | Building services
106 | Adaptation | Develop comms plan for weather warning/alerts and advice | Comms
107 | Adaptation | Consider feasibility of increasing shading, ventilation or cooling equipment in commercial buildings | Building services manager
108 | Adaptation | Consider developing outside respite areas (increased shade and water availability) through increased tree planting in open areas and along paths. | Land scape and ecology
109 | Adaptation | Map areas of potential high impact with potential for major solar gain, ie pre 1960's housing. | Planning
110 | Adaptation | Consideration of measures such as rainwater harvesting, grey water recycling and measures to reduce household water demand and use in social housing (e.g., through installation of water efficiency measures) | Building services |  | Creation of a new tab to incorporate relevant actions to be monitored concurrently with | All action plans are being updated and should be completed by December 2023
111 | Adaptation | Investigate feasibility of installing green rooves on homes, bin stores, bikes sheds etc | Landscape and ecology and building services
112 | Adaptation | Continued engagement and external stakeholders such as LLFA, FIre and rescue etc | Resilience mananger and climate change officer
113 | Adaptation | Engage with stakeholders to dicsuss WHBC impact on river flow and water management and discuuss possible mitigation measures on our land. | Landscape and ecology
114 | Adaptation | Explore additional nature based solutions to sequester carbon to offset any unabated emissions in order to acheive our net zero target. | Landscape and ecology
115 | Adaptation | Investigate the cost of purchasing heat maps to identify hot spots | Climate change officer
116 | Adaptation | Mapping exercise to identify vulnerable areas (based on heat island, LSOA etc) | Climate change officer
117
All actions are measured through SMART targets